PEDIATRIC PAIN RESOURCE NURSE: PROJECT PLAN TEMPLATE

PROJECT NAME:________________________________________________________     UNIT/FOCUS:______________________________________

PROJECT TEAM LEAD: ___________________________________________________      START DATE:_______________     END DATE:____________

| I. PROJECT OVERVIEW |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A. Describe the opportunity. (The opportunity is your vision for the project or goal) |  |  |  |  |  |  |  |
| B. Now describe the objectives. These are actionable steps to attain the project goal. Objectives begin with verbs (identify, document, measure, etc.) and include a measurable result. - Objective 1 - Objective 2 - Objective 3 |  |  |  |  |  |  |  |
| II. PROJECT TEAM |  |  |  |  |  |  |  |
| C. Identify an interdisciplinary team with skills to meet the objectives. Roles include executive sponsor, operational leader, project team lead, early adaptors, advocates, team members, subject matter experts, stakeholders, etc. |  |  |  |  |  |  |  |
| Name, Title |  | Team Role | Time to Commit | Name, Title |  | Team Role | Time to Commit |
| Ex: Dr. Noah Payne, APN |  | Anesthesiology, Team Member | 12 hrs/ quarter | Ex: Dr. Noah Payne, APN |  | Anesthesiology, Team Member | 12 hrs/ quarter |

| III. PROJECT PLAN DETAIL |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| D. Describe the action steps needed for each objective. Actions include one responsible lead, a measureable outcome, start/end date. Actions for each objective are combined to create a comprehensive project plan schedule to monitor progress and report out status to executive sponsors and operational leaders. |  |  |  |  |  |  |
| Objective | Action | Responsible Person | Estimated time needed |  | Other resources needed | Status |
| Ex: Objective 1 | Schedule project team kickoff, provide agenda and team roster | Team Lead | 1 week |  | Help finding a room, order food for kickoff, budget available? | Not started |
|  | Action |  |  |  |  |  |
|  | Action |  |  |  |  |  |
|  | Action |  |  |  |  |  |
|  | Action etc. |  |  |  |  |  |

| IV. STATUS REPORTS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| E. The actions to be completed for each objective form a project schedule. Monitor the schedule to provide updates for the status of each project objective. |  |  |  |  |  |  |
| Objectives | Status (Completed, In Progress, On Hold) | Potential Barrier (Chance of Occurrence: High, Med, Low) | Barrier Mitigation |  | Notes |  |
| Ex: Objective 1 | Completed | None | None |  | Exceptional teamwork, send out recognition |  |
| Ex: Objective 2 | On Hold | New Operational Leader, determine knowledge of project (High) | Determine who needs to meet with the new leader; describe the project and assess interest |  |  |  |

| V. COMMUNICATION/MARKETING PLAN |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| F. While finalizing the team, objectives and actions document the different groups that need to learn about the project to increase awareness, create “buzz” and chatter about the vision, the project and intended benefits. |  |  |  |  |  |  |
| Audience | Key Messages | How to Communicate | Frequency of Communication |  | Lead |  |
| Ex: Leadership | - Project Vision - Project Leaders - Importance of achieving objectives | Leadership Meetings | After introduction; quarterly updates |  | Project Lead and/or Operational Leader |  |
| Ex: Family Board | - Project Vision - Importance of achieving objectives for patients/families | Family Advisory Board meeting | Ask board for recommendations |  | Project Lead with Operational Leaders |  |

| VI. MEETING NOTES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| G. Exercise discipline when taking meeting notes. Use a template so that notes are kept simple and brief, yet accurate and helpful. A well planned agenda simplifies the documentation of meeting notes. Keep a separate log of issues to review/discuss at each meeting. |  |  |  |  |  |  |
| Meeting Date: |  | Next Meeting Date: |  |  |  |  |
| Agenda Topic | Decisions | Actions | Owner |  | Notes |  |