Pediatric Pain PRN FY2015 Project Update: Quarter 1

| Unit – Team | Project | Description- Progress | Needs |
| --- | --- | --- | --- |
| # NICU Lead: [Insert Name] Physician Champion: [Insert Name] Team members: [Insert Name] Social Work [Insert Name] [Insert Name] [Insert Name] | Management of Neonatal Abstinence Syndrome (NAS) | - Poster highlighting risks, pathophysiology, and potential long-term consequences of intrauterine drug exposure. - Education and inter-rater reliability testing of staff to consistently evaluate infants with Finnegan Scale - Journal Club meetings to review treatment options - Developing research study to examine different treatment strategies for NAS and length of stay & length of child-protective services involvement. | - Completed when Posted 1/5/15-2/12/15. - Video of Finnegan to practice and test interrater reliability - Posted 2/15/15, Journal club scheduled for 3/1/15 - Goal: to submit protocol for review end of FY15Q2. |
| PACU Team: Lead: [Insert Name] Physician Champion: [Insert Name] Team members: [Insert Name] PT [Insert Name] [Insert Name] Pain Team advisor: [Insert Name] | Pain Control with Post-op TENs | - Pain Team PT educated surgeons, surgical clinic staff, PACU nurses, Childlife therapists about TENS - Written patient/family education developed and in surgical clinics and preop - Vendor contract pending approval by legal - Measure feasibility: families obtained TENS pre-op, patients tried TENs pre-op, TENS unit use observed during hospitalization, TENs unit use and satisfaction reported during 2-4 week follow-up visit. - Measure effectiveness: Pending feasibility results | - Completed FY 15 Q1 - Completed FY 15 Q1 - Goal: April 15, 2015 - Goal: FY 15 Q2&3 - Goal: FY15 Q4 |
| Ambulatory PRNs Lead: [Insert Name] Physician Champion: [Insert Name] Phlebotomy Champion: [Insert Name] Team members: [Insert Name] [Insert Name] Pain Team advisor [Insert Name] | Topical Anesthetic Use in the Outpatient area | - Pre data obtained in lab 12.3% of ordered draws have topical anesthetic FY14Q4 volume 900 tubes - Academic detailing in clinic to adjust patient clinic flow for use of topical anesthetic 60 minutes before lab draws. Includes: 1) clinical staff, patient, family, registration staff, and phlebotomy education, 2) orders, 3) purposeful wait 4) evaluation - Cost reimbursement: 78% - Employee injuries: FY14Q4: 3 FY15Q1: 1 | - Completed FY14Q4 & FY15Q1 Neurology, Endocrine, ENT, Hematology/Oncology, Genetics, NICU follow-up, Orthopedic FY 15 Q2 Goal: Rheumatology, Developmental Clinic, Allergy - Goal: FY 15 Q2&3 - FY15Q1 19%, 1632 tubes 732 tubes ( 81%) |
| Hematology/ED Lead: [Insert Name] Team members: [Insert Name, Insert Name] [Insert Name, Insert Name] [Insert Name, Insert Name] Physician Champion: [Insert Name, Insert Name] Pain Team advisor [Insert Name] | Time to PCA initiation for VOC pain in patients with sickle cell disease | - Research completed. - Clinical Practice guidelines revised FY14Q2&3 - Conclusion: Teenagers with> 6 hours delay from first opioid in ED to PCA initiation had significantly longer Length of stay (>48 hours) regardless of frequency of hospitalizations for VOC and opioid tolerance. | - Grand Round FY14Q4 - Poster at APHON FY15Q1 - Manuscript in development editor and graphic artist needed - Goal: Submit to APHON Journal End of FY15Q3 |
| # PICU Lead: [Insert Name] Team members: [Insert Name, Insert Name] [Insert Name, Insert Name] [Insert Name, Insert Name] [Insert Name, Insert Name] Pain Team advisor [Insert Name] | Multi-site children's hospital PICU Pain Prevalence study | The purpose of this multi-site research study is to take part in a national multi-site point-prevalence study evaluating pain in the PICU. Data will be collected at three time points. Data collection includes chart review and data extraction, direct care nurse interview, patient/family interview if able within 24 hours of last data extracted. Results will be DE-identified and pooled with other study sites. Funding for data will support PRN program. | - Completion of human subjects protection training - Letter of support - Selection as study site - IRB approval of protocol - Data entry Training |
| 2015 Initiatives |  |  |  |
| ALL PRNs Lead: [Insert Name] Team members: ALL Pain PRNs Pain Team advisor [Insert Name] | Quarterly NDNQI Pain prevalence study & standardizing audits across facility | - QI - PRNs instructed in audit procedure using Epic - Wrote up procedures & clarified interpretations - Each unit PRN to present results to their unit - Next audit End of FY15Q3 | - Epic Access for Offsite NICU - Results and benchmarks each quarter. - Develop PICU documentation standards for pain |
| ALL PRNs Lead: [Insert Name] Team members: ALL Pain PRNs Pain Team advisor [Insert Name] | Pain Scales Update/Education | - Developed standardized presentation for multiple groups (i.e. leadership, educators ect.) to ensure congruent organizational understanding of tools. - PRNs Education provided 3/18/15 with regards to their responsibilities with education rollout across organization. | - Nursing Grand Rounds 3/31/15 - Goal: Unit education by May 1 - Monitor Standards adherence for FY15Q2-4 |